## Form 6
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE SECOND QUARTER, CY 2018
Province: LA UNION
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Supplementary Feeding Program | La Union | 900000 | 2017-12-01 | 2018-12-31 | 6.143% | 55286.92
LGSF-Assistance to Indigent Individuals or Families | La Union | 8000000 | 2017-10-01 | 2018-09-30 | 82.99% | 6639000
Performance Challenge Fund - Procurement of One Mini Bus for Tourism and Development | La Union | 4000000 | 2017-07-01 | 2018-09-30 | 99.98% | 3999260
Performance Challenge Fund - Procurement of Two Rescue Vehicle | La Union | 3000000 | 2018-06-01 | 2018-09-30 | 0% | 0
LGSF-CMGP-Rehabilitation & Improvement of Dumarang-Carcarmay-Cabalitocan (Ubbog-Paagan) Road | La Union | 39000000 | 2017-09-20 | 2018-05-12 | 94.5% | 31368948.54 | 85 calendar days | under time suspension
LGSF-CMGP-Rehabilitation, Improvement, Upgrading of Rosario-Tubao Road | La Union | 47000000 | 2017-11-15 | 2018-07-07 | 80% | 28077800 | 61 calendar days | under time suspension
LGSF-CMGP-Rehabilitation, Improvement, Upgrading of Casilagan-Bail Road | La Union | 9870265 | 2017-09-20 | 2017-12-20 | 100% | 9870265 | 30 calendar days | under time suspension
LGSF-CMGP-Rehabilitation and Improvement of Bacnotan-San Gabriel Road | La Union | 16316528 | 2018-05-18 | 2019-01-13 | 0.5% | 0 | 31 calendar days | under time suspension
LGSF-CMGP-Rehabilitation and Improvement of Bangar-Castro Road | La Union | 20000000 | 2018-05-18 | 2019-02-02 | 0.45% | 0 | 31 calendar days | under time suspension
LGSF-CMGP-Rehabilitation and Improvement of Santol-San Gabriel Road | La Union | 30000000 | 2018-06-18 | 2019-02-12 | 0% | 0 | 31 calendar days | under time suspension
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  |  | Approved by:
ATTY. ALBERT F. PADILLA, CPA | [5 empty] | FRANCISCO EMMANUEL R. ORTEGA III
Provincial Accountant | [5 empty] | Provincial Governor

## Sheet1
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FIRST QUARTER, CY 2019
Province: LA UNION
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Performance Challenge Fund - Procurement of Two Rescue Vehicle | La Union | 7000000 | 2019-01-31 | 2019-12-31 | 0% | 0
Medical Assistance Program | La Union | 5158734 | 2018-01-09 | 2019-12-31 | 61.57% | 3176349.89
Construction of Communal Toilets in Coastal Areas | La Union | 800000 | 2019-01-01 | 2019-12-31 | 0% | 0
Delivery of Basic Health Services to Indigenous Cultural Communities | La Union | 200000 | 2018-01-01 | 2019-06-30 | 38% | 76000
Provincial Malaria Elimination & Response/Sustenance of the Malaria Status of the Province | La Union | 1000000 | 2019-01-31 | 2019-12-31 | 0% | 0
Rice Achievers Award 2015-2016 | La Union | 4000000 | 2018-01-01 | 2019-12-31 | 40.03% | 1601229
LGSF-Assistance to Indigent Individuals or Families | La Union | 8000000 | 2017-10-01 | 2019-06-30 | 98.49% | 7879000
LGSF-Assistance to Indigent Individuals or Families | La Union | 7000000 | 2019-01-31 | 2019-12-31 | 0% | 0
LGSF-Assistance to Indigent Individuals or Families | La Union | 25000000 | 2019-01-31 | 2019-12-31 | 31.96% | 7989200
LGSF-CMGP-Rehabilitation and Improvement of Bacnotan-San Gabriel Road | La Union | 16316528 | 2018-05-18 | 2019-01-13 | 100% | 12218614.21 | 75 calendar days
LGSF-CMGP-Rehabilitation and Improvement of Bangar-Castro Road | La Union | 20000000 | 2018-05-18 | 2019-06-22 | 68.25% | 7696848.3 | 215 calendar days
LGSF-CMGP-Rehabilitation and Improvement of Santol-San Gabriel Road | La Union | 30000000 | 2018-06-18 | 2019-06-15 | 71.6% | 15471637.9 | 198 calendar days
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  |  | Approved by:
ATTY. ALBERT F. PADILLA, CPA | [5 empty] | FRANCISCO EMMANUEL R. ORTEGA III
Provincial Accountant | [5 empty] | Provincial Governor